## Decisions needed
item | current value | decision needed | reviewer_decision | reviewer_comment
Evidence freeze date | TBC at G0 (to be set just after this year's Commission enlargement package) | Set the date (G0 cannot pass while it is TBC)
Target country | North Macedonia (MKD) | Approve
Thematic scope | (a) All of Chapter 2, Freedom of movement for workers (Cluster 2, Internal market); (b) the technology and AI theme: recommendations materially relating to the areas listed in `taxonomy/themes.csv` (theme group `TECH`), wherever they occur in the accession material. Incidental references to technology are out of scope. The full analytical chain is followed for every issue originating from an in-scope Chapter 2 item or technology and AI recommendation. Material outside (a) and (b) is out of scope unless it is needed to follow the chain of an issue already in scope. | Approve
Time window | 2020-01-01 to the evidence freeze date; earlier material only by logged exception where needed to understand the origin or evolution of an in-scope issue | Approve
Language | English primary; Macedonian or Albanian only for core relevant sources with no suitable English version, each recorded in the register; machine translation flagged and capped at Medium confidence | Approve
Comparator scope | Run 1b only: two or three reform issues selected at G6, with two or three comparator countries each, approved at G1b | Approve
Formal gate approvers | Formal gate approvers: Sofia (all gates); Sofia and George together (G6, G6b and G7) | Approve
Alpha reviewers | George reviews the developing product and the review page throughout the run, outside the formal gates. George's feedback reaches Sofia separately; material points are recorded in the alpha learning log | Approve
Theme list | 1.0 (`taxonomy/themes.csv`) | Approve (sheet 'Theme list')
Codebooks | 1.2 (Codebooks 1 to 6), 1.1 (Codebook 7) | Approve
Data dictionary and evidence schema | 1.1 (29 Oct 2026); schema 1.1 (29 Oct 2026) | Approve
Extraction, classification and judgement rules | 0.1b (to be revised at G3); 0.1b; 0.1b | Approve as drafts for use until G3, G5 and G6
Mechanism list | 0.1a draft (approved at G4) | Note only: approved at G4
Helper tools | 1.0.0 for all seven tools (`hash_file.py`, `next_id.py`, `convert_to_text.py`, `verify_quotes.py`, `validate_data.py`, `export_review.py`, `build_review_page.py`); 40 of 40 stage 0 tests passed on 29 Oct 2026 (`tools/tests/last_report.csv`); dependencies in `tools/requirements.txt`; text recognition with Tesseract 5.3.4 (eng, mkd, sqi) | Approve (sheet 'Tools')
Active limits | LIM-0008, LIM-0009, LIM-0010, LIM-0011, LIM-0012, LIM-0013 | Approve (sheet 'Active limits')
Decisions behind this configuration |  | Confirm the decisions taken for this run (sheet 'Decision register')
Alpha lessons | ALN-0001, ALN-0002, ALN-0003 | Set a status for each (sheet 'Alpha lessons')

## Run record
field | value
Run ID | RUN-2026-01
Current stage | 0 Run setup (started 2026-10-29; update at the start of every stage, for example `9 Classify and link` or `1b step 3`)
Purpose | Alpha product and methodology test. Run 1 produces a North Macedonia diagnostic (run 1a) and a comparator pilot (run 1b), and tests the end-to-end workflow, source collection and processing, extraction and classification, taxonomy and matching, the human review gates, assessment and judgement, outputs, and the usefulness of the review page. Lessons are recorded in the alpha learning log to inform scaling to further chapters, clusters and countries
Target country | North Macedonia (MKD)
Thematic scope | (a) All of Chapter 2, Freedom of movement for workers (Cluster 2, Internal market); (b) the technology and AI theme: recommendations materially relating to the areas listed in `taxonomy/themes.csv` (theme group `TECH`), wherever they occur in the accession material. Incidental references to technology are out of scope. The full analytical chain is followed for every issue originating from an in-scope Chapter 2 item or technology and AI recommendation. Material outside (a) and (b) is out of scope unless it is needed to follow the chain of an issue already in scope.
Comparator scope | Run 1b only: two or three reform issues selected at G6, with two or three comparator countries each, approved at G1b
Time window | 2020-01-01 to the evidence freeze date; earlier material only by logged exception where needed to understand the origin or evolution of an in-scope issue
Evidence freeze date | TBC at G0 (to be set just after this year's Commission enlargement package)
Language | English primary; Macedonian or Albanian only for core relevant sources with no suitable English version, each recorded in the register; machine translation flagged and capped at Medium confidence
Reviewers | Formal gate approvers: Sofia (all gates); Sofia and George together (G6, G6b and G7)
Alpha reviewers | George reviews the developing product and the review page throughout the run, outside the formal gates. George's feedback reaches Sofia separately; material points are recorded in the alpha learning log
Review page | `index.html` in the repository root, generated by `tools/build_review_page.py` from 29 Oct 2026
Alpha learning log | `runs/RUN-2026-01/alpha_learning_log.csv`
Codebooks version | 1.2 (Codebooks 1 to 6), 1.1 (Codebook 7)
Extraction rules version | 0.1b (to be revised at G3)
Classification rules version | 0.1b
Judgement rules version | 0.1b
Theme list version | 1.0 (`taxonomy/themes.csv`)
Taxonomy version | none yet (created at G4)
Mechanism list version | 0.1a draft (approved at G4)
Data dictionary version | 1.1 (29 Oct 2026)
Evidence schema version | 1.1 (29 Oct 2026)
Tools versions | 1.0.0 for all seven tools (`hash_file.py`, `next_id.py`, `convert_to_text.py`, `verify_quotes.py`, `validate_data.py`, `export_review.py`, `build_review_page.py`); 40 of 40 stage 0 tests passed on 29 Oct 2026 (`tools/tests/last_report.csv`); dependencies in `tools/requirements.txt`; text recognition with Tesseract 5.3.4 (eng, mkd, sqi)
Started | 2026-10-29 (stage 0)
Closed

## Active limits
limit_id | run_id | limit_type | description | applies_to | reason | temporary_or_permanent | decided_by | decided_on | gate_id | revisit_in | status
LIM-0008 | RUN-2026-01 | country | North Macedonia (MKD) only; comparator evidence only for the 2 to 3 issues selected for run 1b | all | Decision A5: pilot country changed from Serbia before G0; replaces LIM-0001 | temporary | Sofia | 2026-10-29 |  | RUN-2026-01 G8 | active
LIM-0009 | RUN-2026-01 | thematic | Run 1 covers all of Chapter 2 (Freedom of movement for workers) plus the technology and AI theme: recommendations materially relating to the areas in taxonomy/themes.csv wherever they occur; incidental references to technology are out of scope; the full analytical chain is followed for every issue originating from an in-scope Chapter 2 item or technology and AI recommendation | all | Decision A6; replaces LIM-0002 | temporary | Sofia | 2026-10-29 |  | RUN-2026-01 G8 | active
LIM-0010 | RUN-2026-01 | thematic | Material outside Chapter 2 and the technology and AI theme is out of scope unless it is needed to follow the analytical chain of an issue already in scope; there is no list of deferred chapters | all | Decision A9; replaces LIM-0003 and LIM-0004 | temporary | Sofia | 2026-10-29 |  | RUN-2026-01 G8 | active
LIM-0011 | RUN-2026-01 | time | Evidence from 2020-01-01 to the evidence freeze date; earlier material only by logged exception where needed to understand the origin or evolution of an in-scope issue | all | Decision A7; replaces LIM-0005 | temporary | Sofia | 2026-10-29 |  | RUN-2026-01 G8 | active
LIM-0012 | RUN-2026-01 | language | English primary; Macedonian or Albanian only for core relevant sources with no suitable English version; each such source recorded in the register; machine translation flagged and capped at Medium confidence | all | Decision A8; no reviewer who reads Macedonian or Albanian is named for run 1; replaces LIM-0006 | temporary | Sofia | 2026-10-29 |  | When a reviewer who reads the source language is available | active
LIM-0013 | RUN-2026-01 | analytical | No interactive dashboard in run 1 (no country or thematic views); a single static read-only review page (index.html) surfaces validated material and labelled work in progress; outputs remain internal analyst products | all | Decisions E4 as amended by E7; replaces LIM-0007 | temporary | Sofia | 2026-10-29 |  | After run 1 | active

## Superseded limits
limit_id | run_id | limit_type | description | applies_to | reason | temporary_or_permanent | decided_by | decided_on | gate_id | revisit_in | status
LIM-0001 | RUN-2026-01 | country | Serbia only; comparator evidence only for the 2 to 3 issues selected for run 1b | all | Decision A1: test the methodology in a manageable setting | temporary | Sofia | 2026-10-23 |  | RUN-2026-01 G8 | superseded
LIM-0002 | RUN-2026-01 | thematic | Run 1 covers Chapter 5 (Public procurement) only | all | Decision A2 as modified on 23 Oct 2026: one chapter for the first run | temporary | Sofia | 2026-10-23 |  | RUN-2026-01 G8 | superseded
LIM-0003 | RUN-2026-01 | thematic | Chapter 15 (Energy) deferred | chapter:15 | Decision A2: expand only after run 1 is tested | temporary | Sofia | 2026-10-23 |  | Next run | superseded
LIM-0004 | RUN-2026-01 | thematic | Chapter 23 rule-of-law sub-area deferred | chapter:23 | Decision A2: expand only after run 1 is tested | temporary | Sofia | 2026-10-23 |  | Next run | superseded
LIM-0005 | RUN-2026-01 | time | Evidence from 2014 to the evidence freeze date; older documents by logged exception only | all | Decision A3: opening of accession negotiations in 2014 | temporary | Sofia | 2026-10-23 |  | RUN-2026-01 G8 | superseded
LIM-0006 | RUN-2026-01 | language | English primary; Serbian only for core documents with no English version; machine translation capped at Medium confidence | all | Decision A4; no Serbian-speaking reviewer available | temporary | Sofia | 2026-10-23 |  | When a Serbian-speaking reviewer is available | superseded
LIM-0007 | RUN-2026-01 | analytical | No interactive dashboard in run 1; outputs are internal analyst products | all | Decision E4 | temporary | Sofia | 2026-10-23 |  | After run 1 | superseded

## Theme list
theme_code | theme_group | label | definition | material_examples | incidental_examples | status | version
TECH-AI | TECH | Artificial intelligence | The development, use, regulation or oversight of artificial intelligence systems, including alignment with EU rules on artificial intelligence. | Adopting rules on high-risk AI systems; designating an AI supervisory authority | A general reference to new technologies in a strategy title | approved | 1.0
TECH-DGOV | TECH | Digital government and digital public services | Electronic administration and public services delivered or managed digitally, including e-government portals and online procedures. | Making social security entitlements available through an online service | Asking a ministry to publish a report on its website | approved | 1.0
TECH-INFRA | TECH | Digital infrastructure and connectivity | Broadband, mobile and other electronic communications networks, and access to them. | Rolling out broadband to rural areas; allocating 5G spectrum | Mentioning internet access in a description of living conditions | approved | 1.0
TECH-DATA | TECH | Data and data governance | The collection, protection, quality, sharing, reuse and governance of data, including personal data protection and open data. | Aligning personal data protection law; setting up a register with reliable data | A recommendation to improve statistics without reference to data systems or governance | approved | 1.0
TECH-CYBER | TECH | Cybersecurity | The security of networks and information systems, including incident response capacity and cybersecurity rules. | Establishing a national computer security incident response team | A general reference to security | approved | 1.0
TECH-EID | TECH | Digital identity | Electronic identification, electronic signatures and other trust services. | Introducing a national electronic identification scheme | Requiring identity documents to be checked | approved | 1.0
TECH-INTEROP | TECH | Interoperability and electronic systems | The ability of information systems to exchange data, and the electronic systems used to run or connect administrative processes, including connection to EU systems. | Connecting to an EU electronic exchange system; adopting an interoperability framework | Mentioning that information is shared between institutions without reference to a system | approved | 1.0
TECH-DIGI | TECH | Digitalisation of government or economic activity | Moving government processes or economic activity onto digital means, including digital transformation programmes and the digitalisation of businesses. | Digitalising company registration; a programme to digitalise small businesses | A passing reference to modernisation | approved | 1.0

## Decision register
ID | Group | Decision | Status | Outcome
A1 | Scope | How comparator countries are handled in run 1 | Amended by A5 (target country) | Run 1 split: 1a Serbia diagnostic; 1b comparator pilot on 2 to 3 analyst-selected issues, comparator evidence tagged as such, expansion logged as deliberate
A2 | Scope | Thematic scope of run 1 | Superseded by A6 and A9 | One chapter for run 1: Chapter 5 Public procurement. Chapter 15 Energy and a Chapter 23 sub-area deferred; expand only after run 1 is tested
A3 | Scope | Time window and evidence freeze date | Superseded by A7 (freeze date rule kept) | Evidence from 2014 onward; fixed freeze date just after this year's Commission enlargement package (set at G0); older documents by logged exception only
A4 | Scope | Language policy | Superseded by A8 | English primary; Serbian only for core documents with no English version; original quote plus flagged machine translation; no Serbian-speaking reviewer available, so machine-translated evidence is capped at Medium confidence and listed in the limits report
B1 | Concepts | One canonical analytical chain and shared vocabulary | Approved | Ten-link chain: EU requirement, reform issue, country response, implementation, outcome, unresolved gap, comparator evidence, lesson, priority, policy option. "Finding/stated" = what a source says; "judgement/assessed" = what we conclude
B2 | Concepts | Unit of analysis and record types | Approved | Evidence item = one claim, one information type, exact quote and location, with separate speaker and subject actors. Layered records: sources, evidence items, analytical entities, links (incl. corroborates/contradicts), judgements
B3 | Concepts | Which object each judgement attaches to | Approved | Each judgement attaches to the object it describes. Adds relevance and unresolved gap. Each judgement records value, reason, cited evidence items, made by, review status, codebook version
C1 | Sources | How the agent discovers and acquires documents | Approved | Requirements-led acquisition, analyst approval at G1, official domains preferred, originals plus page-numbered text, webpage snapshots, OCR and translation flagged, no bypassing of paywalls or logins, every failure logged, manual drop-in folder
C2 | Sources | Master source register fields | Approved | Every document ever considered, with status and reason (full field list in schemas/data_dictionary.md). Separate limits log for scope-level limits
C3 | Sources | Folder structure and naming rules | Approved | sources/<country>/<family>/originals and /text; file name = source ID plus short label, no spaces
C4 | Sources | Source quality method; confidence and relevance | Approved | Source quality per source per topic, High/Medium/Low from six factors plus one-line reason. Confidence and relevance on the same levels with own criteria. Never merged. AI proposes; analyst reviews by exception at G2
C5 | Sources | Civil society monitoring as a fifth source family | Approved | New family CSO with its own use, limits and default guidance
D1 | Data | CSV, JSON or a combination | Approved | CSV for anything reviewed or edited; JSON for evidence items, one file per source; spreadsheet exports at gates; any database rebuilt from files
D2 | Data | Identifier scheme | Approved | Permanent semi-readable IDs, never reused or changed; reform issue IDs country-neutral
D3 | Data | Extraction and classification as separate passes | Approved | Pass 1 extraction; pass 2 classification; taxonomy changes re-run pass 2 only
D4 | Data | Taxonomy and problem mechanisms | Approved | Hybrid, two levels; agent proposes, analyst approves; versioned; retired IDs never reused
D5 | Data | Minimum set of matching fields | Amended by D6 (cross-cutting themes) | Controlled fields on every item; no free-text keywords; cross-chapter themes deferred
E1 | Process | Sample parse and review | Approved | 10 to 12 documents across five families; three hand-coded passages; automatic quote check; checklist; max two refinement loops; EU family first, then taxonomy, then the rest
E2 | Process | Control gates; AI authority | Approved | Gates G0 to G8, all blocking, gate log; three tiers of authority. Reviewers: Sofia at all gates; Sofia and George at G6, G6b and G7
E3 | Process | Future runs and versioning | Approved | Incremental versioned runs; unchanged sources reused; updates kept as versions; targeted re-runs; validated judgements never overwritten; G8 run review feeds codebook changes
E4 | Process | What run 1 produces | Amended by E7 (review page) | Internal analyst products; draft policy options only for run 1b issues; no dashboard in run 1; new Codebook 7 (Outputs)
A5 | Scope | Pilot country for run 1 | Approved | North Macedonia (MKD) replaces Serbia as the target country. The run 1a and 1b structure of A1 is unchanged
A6 | Scope | Thematic scope of run 1 | Approved | (a) All of Chapter 2, Freedom of movement for workers; (b) recommendations materially relating to technology and AI wherever they occur in the accession material. Theme areas: artificial intelligence; digital government and digital public services; digital infrastructure and connectivity; data and data governance; cybersecurity; digital identity; interoperability and electronic systems; digitalisation of government or economic activity. Incidental references to technology are out of scope. The full analytical chain is followed for every issue originating from an in-scope Chapter 2 item or technology and AI recommendation
A7 | Scope | Time window | Approved | Evidence from 1 January 2020 to the evidence freeze date; freeze date rule from A3 kept; earlier evidence only by logged exception where needed to understand the origin or evolution of an in-scope issue
A8 | Scope | Language policy | Approved | English primary; Macedonian where a core relevant source has no suitable English version; Albanian-language official material not excluded automatically: where a core relevant source exists only in Albanian it is recorded and the same translation and confidence safeguards apply; machine translation flagged and capped at Medium confidence
A9 | Scope | Deferred chapters and material outside the scope | Approved | The Serbia-era deferral of Chapter 15 and a Chapter 23 sub-area is removed and no replacement list is kept. Material outside Chapter 2 and the technology and AI theme is out of scope unless it is needed to follow the analytical chain of an issue already in scope
D6 | Data | Cross-cutting themes | Approved | Controlled theme list in `taxonomy/themes.csv` with a materiality test; evidence items carry `themes` and `scope_basis` (chapter, theme, chain, exception); pass 2 scope check with `out_of_scope` status; theme columns added to the source requirements, source register and reform issues; brought forward from the deferral in D5 because A6 requires it
E5 | Process | Handling the pilot change | Approved | RUN-2026-01 kept, as no acquisition, extraction or analysis had taken place; treated as a pre-G0 configuration change; superseded limits marked `superseded` and replaced by new rows; new versions: codebooks 1.2 (1 to 6) and 1.1 (7), rules 0.1b, data dictionary 1.1, evidence schema 1.1, mechanism list 0.1a, theme list 1.0, ARCHITECTURE.md 1.1
E6 | Process | Purpose of run 1 | Approved | RUN-2026-01 is an alpha product and methodology test. Besides the analysis, it tests the end-to-end workflow, source collection and processing, extraction and classification, taxonomy and matching, human review gates, assessment and judgement, outputs, and the usefulness of the review page. The method stays reusable and country-neutral
E7 | Process | Single HTML review page | Approved | `index.html` in the repository root, intended for later hosting on GitHub Pages. Read-only review interface showing validated material and relevant work in progress, each labelled Validated, Pending review, Proposed, Draft or Not started. Not the formal gate-decision mechanism: decisions stay in the review spreadsheets and the gate log. Generated by `tools/build_review_page.py` once built; rebuilt after each gate decision and when a gate package is prepared. Replaces the "no dashboard" element of E4 for this page only; no interactive country or thematic dashboard in run 1
E8 | Process | Alpha learning log | Approved | `runs/RUN-2026-01/alpha_learning_log.csv` holds curated, material lessons from the alpha, especially for scaling to more chapters, clusters and countries. It cross-references the limits log, decision log, gate log and run notes instead of repeating them. `run_notes.md` stays the low-threshold working diary. The agent proposes rows; Sofia confirms them at gates. Feeds the run review at G8
E9 | Process | George's role in the alpha | Approved | George is an alpha reviewer of the developing product and the review page throughout the run. Formal gate responsibilities are unchanged (Sofia at all gates; Sofia and George at G6, G6b and G7). George's feedback goes to Sofia separately; material feedback is recorded in the alpha learning log and, where relevant, in the decision log, limits log or run record
E10 | Process | Visibility of the repository and review page | Approved | The GitHub repository and the GitHub Pages review page stay public for the alpha. Agreed by Sofia with George on 29 Oct 2026. Treated as settled; not to be reopened unless Sofia asks
F1 | Package | Format of revised codebooks | Approved | Markdown copies in the Claude Code folder (followed by agents) plus Word copies with tracked changes against the 20 Oct originals for human review; Codebook 7 in both forms
F2 | Package | Country neutrality | Approved | Codebooks, procedures and rules use "target country" or "pilot country"; run-specific settings (country, chapters, themes, time window, languages, source hints, area codes) sit in the run record, CLAUDE.md and the limits log

## Alpha lessons
lesson_id | run_id | date_raised | stage | gate | area | lesson_type | description | examples | impact | scaling_dimension | scaling_implication | recommendation | cross_refs | status | decided_at | raised_by | reviewer_decision | reviewer_comment
ALN-0001 | RUN-2026-01 | 2026-10-29 | pre-G0 |  | workflow | change_made | Changing the pilot country from Serbia to North Macedonia before G0 required edits to about thirty files because country, chapter, dates, languages and examples were written into the codebooks, procedures and rules. | codebooks/CB1_project_explanation.md;codebooks/CB3_limits_and_log.md;procedures/P1_setup_and_sources.md;rules/extraction_rules.md | High | countries;chapters | Every new country or chapter would have needed the same sweep. Keeping run-specific settings in the run record, CLAUDE.md and the limits log makes the method reusable. | Keep method documents country-neutral; add a check before each new run that searches the method documents for country, chapter and date terms. | F2;E5;LIM-0001;LIM-0002;LIM-0003;LIM-0004;LIM-0005;LIM-0006 | open |  | agent
ALN-0002 | RUN-2026-01 | 2026-10-29 | pre-G0 |  | taxonomy_matching | methodological_issue | A scope combining one chapter with a cross-cutting theme (technology and AI) could not be expressed with chapter and cluster fields alone, so theme tags planned for a later stage had to be brought forward. | taxonomy/themes.csv;schemas/evidence_item.schema.json | High | chapters;clusters | Scaling across chapters and clusters will need more cross-cutting themes; the materiality test and scope basis need testing at G3 to G5 before more themes are added. | Review how well the materiality test and the out_of_scope check work at G3 and G5 before defining further themes. | D5;D6;A6;run_notes 2026-10-29 | open |  | agent
ALN-0003 | RUN-2026-01 | 2026-10-29 | 0 | G0 | tooling | technical_issue | The helper tools depend on system software (text recognition with Macedonian and Albanian language data, PDF rendering) that was not installed in the working environment and was not recorded anywhere before stage 0. | tools/requirements.txt;tools/tests/last_report.csv | Medium | countries;languages | Each new country or language needs its own text recognition data and a test with a sample in that script before extraction starts. | Keep tools/requirements.txt current; add a scanned sample in each new language to tools/tests/test_tools.py before a new country is added. | run_notes 2026-10-29 | open |  | agent

## Tools
tool | version | tests
hash_file.py | 1.0.0 | 1 passed, 0 failed
next_id.py | 1.0.0 | 6 passed, 0 failed
convert_to_text.py | 1.0.0 | 8 passed, 0 failed
verify_quotes.py | 1.0.0 | 9 passed, 0 failed
validate_data.py | 1.0.0 | 6 passed, 0 failed
export_review.py | 1.0.0 | 4 passed, 0 failed
build_review_page.py | 1.0.0 | 6 passed, 0 failed

## Validation
validate_data output
validate_data 1.0.0: 0 evidence file(s), 0 item(s), 34 CSV row(s)
0 error(s), 0 warning(s)